## Ark2
Project Exam 1
Micropage
André Lekve |  | Project start 24.08 - end 27.09 | August | [7 empty] | September
|  |  | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39
ID | Assignment | Estimated time | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
- | Producing website | 34 days
1 | Work plan (gantt chart, plan report) | 2 days | bar: Week 35 M to Week 35 T
2 | Research (API)/Personae | 2 days | bar: Week 35 W to Week 35 F
3 | Design - Sketching (Prototype) | 2 days | bar: Week 36 M to Week 36 T
4 | Design | 3 days | bar: Week 36 W to Week 36 F
5 | HTML/CSS | 15 days | bar: Week 37 M to Week 37 F; Week 38 M to Week 38 F; Week 39 M to Week 39 F
6 | Testing | 5 days | bar: Week 37 F; Week 38 F; Week 39 F to Week 39 S
7 | Report | 7 days | bar: Week 35 F; Week 36 F; Week 37 F; Week 38 F; Week 39 F to Week 39 S
Brief Planning Report
· Producing website – This shows how many days I’m using on the project.
· Work Plan – Making a Gantt chart and writing a brief planning report.
· Research – Looking at other websites. What colours does these websites use and how is the layout?
· Design - Sketching – Sketching layouts for my website. This assignment is overlapping Research, because I would like to make some sketches while doing research.
· Design – Finding/making a logo, what fonts to use, what colours to use, how the buttons will look etc.
· HTML/CSS – The time spent on coding.
· Testing – Quality control of the website for the different devices.
· Report – I’ll be writing the technical report at the end of each week. This way it’s easier to remember what I have done.